## Sheet1
S.No. | Points | Module | Assignee | Est. time | Actual Time | Staus | RAG | Unit Testing | UAT
1 | Calendar Block to have colour & should have mouse over |  | lalit + varun | 11thsep | 11thsep | closed |  | Not Done
2 | School Holidays through Form to be checked |  | lalit + varun | 11thsep | 11thsep | closed |  | Not Done
3 | Google Data Should give all data & school should have option to choose and pick Holidays |  | lalit + varun | 12th sep | 12th sep | closed |  | Not Done
4 | All Sunday’s should be marked as Holiday & Saturday can be marked by School Admin |  | lalit + varun | 12th sep | 12th sep | closed |  | Not Done
5 | Class Teacher not coming |  | Amit | 11thsep | 09th sep | closed |  | Not Done
6 | Class Room No …..Make it Non Mandatory |  | Amit +Govind | 11th sep | 09th sep | closed |  | Not Done
7 | Academic Subject to be faded and Non Academic to be highlighted in calendar |  | Nainji | 11thsep | 11th sep | closed |  | Not Done
8 | Add 2 Breaks Option and Add Section Periods After Breaks |  | Govind +amit +Nainji | 12th sep | 26th sep | closed |  | Not Done
9 | Coach Time Table View |  | utkarsh | 13th sep | 15th sep | closed |  | Not Done
10 | School to be listed as an Academy Create a Module for Listing |  | utkarsh +amit +nainji | 17th sep | 16th sep | closed |  | Not Done
11 | Committee and Staff to be added in the School – Documentation to be discussed later with Klubba Team |  | To be Discussed | To be discussed with client |  |  |  | Not Done
12 | Remove Extra Classes |  | Govind | 11th sep | 10th sep | closed |  | Not Done
13 | Group should have Clubs and Linkages Group & Club to be made live |  | Amit +Govind | 17th sep | 2023-09-21 | closed |  | Not Done
14 | All Groups & Learner – Data To Be Made Dynamic and Remove Attendance |  | amit+nainji | 17th sep | 25th sep | done |  | Not Done
15 | Add Member and Assign Group UI to be made simpler |  | varun +lalit | 17th sep |  |  |  | Not Done
16 | Bulk Upload Name to be changed to Download Sample and |  | govind+amit | 15thsep | 13th sep | done |  | Not Done
17 | Bulk Student upload should be also have Club / Section / Class Option in bulk upload excel |  | amit+govind | 15th sep | 18th sep | done |  | Not Done
18 | School Listing Module to be added |  | varun+utkarsh | 16thsep | 16th sep | done |  | Not Done
19 | My Transaction should also undergo change in line with listing Module as done for Academy |  | lalit + varun | 23thsep |  | done |  | Not Done
20 | Remove Refer and Earn from School and Academy |  | govind | 11th sep | 11th sep | done |  | Not Done
21 | Academy – Manage Group and Learners to be made Dynamic and Remove Attendance |  | nainji | 2023-09-25 | 26th sep | closed |  | Not Done
22 | Create Event – Banner Needs to be checked for Bigger Screens |  | vinod |  |  |  |  | Not Done
23 | Check Pricing with GST and Without GST |  | utkarsh | 19th sep | 16th sep | done |  | Not Done
24 | Coach Dashboard – Login with School, Academy and as an Individual user and get Dashboard accordingly ….….In Case of Multiple Schools give option to select. |  | nainji+lalit+amit+varun | 2023-10-10 |  | wip |  | Not Done
25 | Group creation by Academy or School is not allowed has to be done by School Admin …….Coach can only create Subgroup and can’t change group allocated by Admin basis time table |  | nainji+lalit+amit+varun | 2023-10-10 |  | wip |  | Not Done
26 | Only Klubba – Planner can be shifted |  | amit+utkarsh | 11th sep | 09th sep | done |  | Not Done
27 | Give Upload Bulk Upload for School |  | mahesh+govind+varun | 16thsep | 16th sep | done |  | Not Done
28 | 1. Package 499 Give Name and Admin can change ……By Default all Paid Users Individuals or Schools will get that basic Package |  | Amit+Nainji | 19th sep | 17th sep | done |  | Not Done
29 | Availability Timing – Should be linked to Timetable. |  | nainji+utkarsh | 11th sep | 11th sep | done |  | Not Done
30 | 1. Zip Code only required Coaching. |  | utkarsh | 11th sep | 11th sep | done |  | Not Done
31 | 1. Show Calendar to Learner |  | amit+utkarsh | 11th sep | 11th sep | done |  | Not Done
32 | 1. Change school calendar to Academic Calendar |  | lalit | 11th sep | 11th sep | done |  | Not Done
33 | Learner Assessment based on tailor made |  | nainji +amit | 25th sep | 26th sep | closed |  | Not Done
34 | Home Page ui changes on foundation |  | vinod sir |  |  |  |  | Not Done
35 | our gallery new page |  | chanchal | 2023-09-15 | 15th sep | done |  | Not Done
36 | coach assessment flow and academy/school assessment discussion |  | To be Discussed | To be discussed with client
37 | Committee in events and school to be either removed or should be linked |  | To be Discussed | To be discussed with client
38 | Images for login screen pending from client |  | client side dependency | Images Pending